## Defect Tracking Log
DEFECT TRACKING LOG
Project Name | Seaview Apartments Prvan Testing
Program Manager | Anis Kazazić, Adnan Ulaković, Omar Čolakhodžić
Project Manager | Anis Kazazić, Adnan Ulaković, Omar Čolakhodžić
Purpose: To ensure that the work product meets specifications for performance, defects must be tracked and fixed. These defects may arise from any Phase, but the majority will arise in the Testing Phase and must be properly captured and tracked through resolution. This form will allow documentation of test defects that must be corrected prior to project completion. Also, this form makes it easier to monitor status of the defect correction progress. This form may be used by any member of the software development team.
< Hover by the red triangle in the top left corner for more detail. Use the Instructions on the next tab to fill out fields.>
Defect No. | Date Created | Created By | Defect Description | PM Process | Lifecycle Phase | Priority | Owner | Assigned Date | Estimated Time to Fix | Status | Resolution | Resolution Date | Actual Time to Fix | Root Cause | Status | Priority | PM | Lifecycle Phase
1 | 3.1.2026. | Anis Kazazić, Adnan Ulaković, Omar Čolakhodžić | 1.Go to https://seaview-apartmani.com/hr 2. Click on "Pošalji upit" button 3. Select date from 4. Select date to < date from 5. Select avaliable apartment 6. Click the "Dalje" button 7. Fill the rest of the form with valid data 8. Click the "Pošalji upit" button Expected result : The following error message is shown : "Datum dolaska mora biti manji od datuma odlaska" Entered value: https://edufit-my.sharepoint.com/:i:/g/personal/omar_colakhodzic_edu_fit_ba/IQCUAauoKyvvQ71wcfWeFZ2aAdblVDnHfWd8zDcFLcY_5is?e=h0ZL4c Response: https://edufit-my.sharepoint.com/:i:/g/personal/omar_colakhodzic_edu_fit_ba/IQCSzQMja7NfRJhPrAYOf-kBAat4aw-LDZIz2gGJtBCADA4?e=7nnSNW | [6 empty] | New |  |  |  |  | New
2 | 3.1.2026. | Anis Kazazić, Adnan Ulaković, Omar Čolakhodžić | 1.Go to https://seaview-apartmani.com/hr 2. Click on "Pošalji upit" button 3. Select date from and date to 4. Select avaliable apartment 5. Set a number of persons to 0 6. Click the "Dalje" button 7. Fill the rest of the form with valid data 8. Click the "Pošalji upit" button Expected result : The following error message is shown : "Minimalan broj osoba je 1" Entered value: https://edufit-my.sharepoint.com/:i:/g/personal/omar_colakhodzic_edu_fit_ba/IQBkmsQZPNmPR7UZLd0610aXAerXJlzklgNy-3U5rcqvSOI?e=T8JTgy Response: https://edufit-my.sharepoint.com/:i:/g/personal/omar_colakhodzic_edu_fit_ba/IQCSzQMja7NfRJhPrAYOf-kBAat4aw-LDZIz2gGJtBCADA4?e=7nnSNW | [6 empty] | New |  |  |  |  | Under Review | High | Opportunity Assessment | Opportunity Assessment
3 | 3.1.2026. | Anis Kazazić, Adnan Ulaković, Omar Čolakhodžić | 1.Go to https://seaview-apartmani.com/hr 2. Click on "Pošalji upit" button 3. Select date from and date to 4. Select avaliable apartment 5. Click the "Dalje" button 6. Enter name and surname longer than 51 characters 7. Fill the rest of the form with valid data 8. Click the "Pošalji upit" button Expected result : The following error message is shown : "Ime i prezime ne smije biti preko 51 karaktera" Entered value: https://edufit-my.sharepoint.com/:i:/g/personal/omar_colakhodzic_edu_fit_ba/IQCCTBTlMjitTq4BnkkfiCOVAY9PYRRRsQhcIlN4Buq0lxM?e=Nx8WHb Response: https://edufit-my.sharepoint.com/:i:/g/personal/omar_colakhodzic_edu_fit_ba/IQCSzQMja7NfRJhPrAYOf-kBAat4aw-LDZIz2gGJtBCADA4?e=7nnSNW | [6 empty] | New |  |  |  |  | In Progress | Medium | Initiating | Concept
4 | 3.1.2026. | Anis Kazazić, Adnan Ulaković, Omar Čolakhodžić | 1.Go to https://seaview-apartmani.com/hr 2. Click on "Pošalji upit" button 3. Select date from and date to 4. Select avaliable apartment 5. Click the "Dalje" button 6. Make sure addres field is null 7. Fill the rest of the form with valid data 8. Click the "Pošalji upit" button Expected result : The following error message is shown : "Adresa ne smije biti prazna" Entered value: https://edufit-my.sharepoint.com/:i:/g/personal/omar_colakhodzic_edu_fit_ba/IQCa6JKxx73QT7e_2g9E8hY5AUYkRo8__U6FD23xcVdYMEU?e=CkeiH5 Response: https://edufit-my.sharepoint.com/:i:/g/personal/omar_colakhodzic_edu_fit_ba/IQCSzQMja7NfRJhPrAYOf-kBAat4aw-LDZIz2gGJtBCADA4?e=7nnSNW | [6 empty] | New |  |  |  |  | Completed | Low | Planning | Requirements
5 | 3.1.2026. | Anis Kazazić, Adnan Ulaković, Omar Čolakhodžić | 1.Go to https://seaview-apartmani.com/hr 2. Click on "Pošalji upit" button 3. Select date from and date to 4. Select avaliable apartment 5. Click the "Dalje" button 6. Enter invalid address (example: #$%) 7. Fill the rest of the form with valid data 8. Click the "Pošalji upit" button Expected result : The following error message is shown : "Molimo unesite validnu adresu" Entered value: https://edufit-my.sharepoint.com/:i:/g/personal/omar_colakhodzic_edu_fit_ba/IQDinRvjkwdvTK_KyKCt1DvgAR6ZlcvnBz4-4FMq3JbTwKQ?e=zQXNAZ Response: https://edufit-my.sharepoint.com/:i:/g/personal/omar_colakhodzic_edu_fit_ba/IQCSzQMja7NfRJhPrAYOf-kBAat4aw-LDZIz2gGJtBCADA4?e=7nnSNW | [6 empty] | New | [6 empty] | Executing/Controlling | Design
6 | 3.1.2026. | Anis Kazazić, Adnan Ulaković, Omar Čolakhodžić | 1.Go to https://seaview-apartmani.com/hr 2. Click on "Pošalji upit" button 3. Select date from and date to 4. Select avaliable apartment 5. Click the "Dalje" button 6. Make sure the city field is null 7. Fill the rest of the form with valid data 8. Click the "Pošalji upit" button Expected result : The following error message is shown : "Grad ne smije biti prazan" Entered value: https://edufit-my.sharepoint.com/:i:/g/personal/omar_colakhodzic_edu_fit_ba/IQD8JwbhdiP-Q55d19fHuf-XARvS9PTZFpJTiV_aewuJea0?e=3T0cxF Response: https://edufit-my.sharepoint.com/:i:/g/personal/omar_colakhodzic_edu_fit_ba/IQCSzQMja7NfRJhPrAYOf-kBAat4aw-LDZIz2gGJtBCADA4?e=7nnSNW | [6 empty] | New | [6 empty] | Closing | Development
7 | 3.1.2026. | Anis Kazazić, Adnan Ulaković, Omar Čolakhodžić | 1.Go to https://seaview-apartmani.com/hr 2. Click on "Pošalji upit" button 3. Select date from and date to 4. Select avaliable apartment 5. Click the "Dalje" button 6. Enter invalid city (example: #$%) 7. Fill the rest of the form with valid data 8. Click the "Pošalji upit" button Expected result : The following error message is shown : "Molimo unesite validan grad" Entered value: https://edufit-my.sharepoint.com/:i:/g/personal/omar_colakhodzic_edu_fit_ba/IQAPhuH-MpLlTZVqHJtTkMaTAQlifD6a4CeBqlKQ1fGC-Uk?e=dhMPEm Response: https://edufit-my.sharepoint.com/:i:/g/personal/omar_colakhodzic_edu_fit_ba/IQCSzQMja7NfRJhPrAYOf-kBAat4aw-LDZIz2gGJtBCADA4?e=7nnSNW | [6 empty] | New | [7 empty] | Testing
8 | 3.1.2026. | Anis Kazazić, Adnan Ulaković, Omar Čolakhodžić | 1.Go to https://seaview-apartmani.com/hr 2. Click on "Pošalji upit" button 3. Select date from and date to 4. Select avaliable apartment 5. Click the "Dalje" button 6. Enter invalid telephone (example: #$%) 7. Fill the rest of the form with valid data 8. Click the "Pošalji upit" button Expected result : The following error message is shown : "Molimo unesite validan telefon" Entered value: https://edufit-my.sharepoint.com/:i:/g/personal/omar_colakhodzic_edu_fit_ba/IQDx6MjSQ1oVQ7XqjWqeccKEAcVUlIvXuitMR_eSK5HfDok?e=edktLO Response: https://edufit-my.sharepoint.com/:i:/g/personal/omar_colakhodzic_edu_fit_ba/IQCSzQMja7NfRJhPrAYOf-kBAat4aw-LDZIz2gGJtBCADA4?e=7nnSNW | [6 empty] | New | [7 empty] | Documentation and Training
9 | 3.1.2026. | Anis Kazazić, Adnan Ulaković, Omar Čolakhodžić | 1.Go to https://seaview-apartmani.com/hr 2. Click on "Pošalji upit" button 3. Select date from and date to 4. Select avaliable apartment 5. Click the "Dalje" button 6. Enter a note that is longer than 2000 characters 7. Fill the rest of the form with valid data 8. Click the "Pošalji upit" button Expected result : The following error message is shown : "Molimo unesite napomenu kraću od 2000 karaktera" Entered value: https://edufit-my.sharepoint.com/:i:/g/personal/omar_colakhodzic_edu_fit_ba/IQD1DJ3aovfGQ6aJJtRa_P_IAVZAQ38gSqEZWrCHl9882Ww?e=A7LHlF Response: https://edufit-my.sharepoint.com/:i:/g/personal/omar_colakhodzic_edu_fit_ba/IQCSzQMja7NfRJhPrAYOf-kBAat4aw-LDZIz2gGJtBCADA4?e=7nnSNW | [6 empty] | New | [7 empty] | Deployment
10 | 3.1.2026. | Anis Kazazić, Adnan Ulaković, Omar Čolakhodžić | 1.Go to https://seaview-apartmani.com/hr 2. Click on "Pošalji upit" button 3. Select date from and date to 4. Select avaliable apartment 5. Set a number of persons to -5 6. Click the "Dalje" button 7. Fill the rest of the form with valid data 8. Click the "Pošalji upit" button Expected result : The following error message is shown : "Minimalan broj osoba je 1" Entered value: https://edufit-my.sharepoint.com/:i:/g/personal/omar_colakhodzic_edu_fit_ba/IQBxqHgti9B2SLvnPsSa0oe5AR8VqYtNRbPnDV65HSw1_wo?e=KmWvUi Response: https://edufit-my.sharepoint.com/:i:/g/personal/omar_colakhodzic_edu_fit_ba/IQCSzQMja7NfRJhPrAYOf-kBAat4aw-LDZIz2gGJtBCADA4?e=7nnSNW | [6 empty] | New | [7 empty] | Post-Deployment
11
12
13
14
15
16
17
18
Note on E10: ====== ID#AAAAn_rmfi0 Julie Arnold (2023-01-09 19:26:29) Choose from the drop down box.
Note on F10: ====== ID#AAAAn_rmfiw John Casey (2023-01-09 19:26:29) Choose from the drop down box.
Note on G10: ====== ID#AAAAn_rmfio Julie Arnold (2023-01-09 19:26:29) Choose from the drop down list
Note on K10: ====== ID#AAAAn_rmfis Julie Arnold (2023-01-09 19:26:29) Choose from the drop down list.

## Defect Tracking Log Instruc
Defect Tracking Log Instructions
Field | Description
Defect Number | Unique identifier for the defect, i.e., 1,2 etc.
Date Created | Date on which the defect was initially reported and logged.
Created By | Name of the person who reported the defect.
Defect Description | Description of the defect. State the subsystem, area, or other part of the product in which the defect occurs or which is affected by the defect.
PM Process | Choose the Project Management Process this defect was reported for: Opportunity Assessment, Initiating, Planning, Executing/Controlling and Closing.
Lifecycle Phase | List the lifecycle this defect was reported for. The Software Development lifecycle is: Opportunity Assessment, Concept, Requirements, Design, Development, Testing, Documentation and Training, Deployment and Post Deployment.
Priority | The priority code indicates the impact of this defect on the project:
H = High (extremely important, the project cannot be successful without this defect being resolved)
M = Medium (important to project success, but a work around exists)
L = Low (desirable, but with little impact to project success if the defect is not resolved)
Owner | Name of the person who is responsible for fixing the defect.
Assigned Date | Date on which the defect was assigned for resolution.
Estimated Time To Fix | Estimated amount of time required to correct the defect. If applicable list in hours, not days.
Status | Current status of the defect: New, In Progress, Under Review and Completed.
Resolution | Description of the defect’s resolution.
Resolution Date | Date on which the defect is to be resolved (or is resolved depending upon its status).
Actual Time to Fix | Actual time required to correct the defect.
Root Cause Description | State the cause of the defect (for example, communication, oversight, transcription, education, process, bad code.).